## 1. RCCA Worksheet Template
|  |  | Root Cause/Corrective Action (RCCA) Worksheet | [9 empty] | Date Issued
1. Build the Team |  |  |  |  | 2. Define the Problem |  |  | (Describe the problem in a concise statement that provides a clear definition of the issue/concern)
Lead
Team Members
3. Containment Action |  | (What immediate action(s) need to be taken to isolate, contain, screen, and provide interim resolution to the problem? Insert additional rows as needed)
Action Items | [6 empty] | Target Completion Date |  |  |  | Responsible Person(s) |  |  | Actual Completion Date
4. Identify Root Cause |  |  |  |  | 4a. Fishbone Diagram |  |  |  | 1) Define and list all contributing factors 2) Highlight in yellow the contributing factors that seem to have the biggest effect 3) Highlight in green the human factors that were considered in the analysis.
| Method |  |  | People |  |  | Environment
Problem / Defect
| Material |  |  | Machine |  |  | Measurement
Fishbone Cause |  |  |  |  | 4b. 3 x 5 Why |  |  |  |  | For each highlighted cause above, perform a 3x5 why analysis
If more than one cause is highlighted, duplicate sections 4b and 4c for each
Direct Cause (What immediate cause led to the nonconformance?)
Detection Cause (Why was the nonconformance not caught by inspection, test, or other process controls?)
Systemic Cause (What core processes, systems, procedures, etc. allowed the nonconformance to occur?)
4c. Identified Root Causes
|  | Direct Root Cause |  |  |  | Detection Root Cause | [5 empty] | Systemic Root Cause
5. Identify and Define Corrective Actions |  |  |  | (Generate permanent corrective action(s) for the identified root causes. Insert additional rows as needed)
Action Items | [6 empty] | Target Completion Date |  |  |  | Responsible Person(s) |  |  | Actual Completion Date
6. Corrective Action Verification Plan |  |  |  | (What actions will be completed to ensure that the corrective action(s) are effective? Insert additional rows as needed)
Corrective Action |  |  |  | How will it be verified? |  |  | Target Completion Date |  |  |  | Responsible Person(s) |  |  | Acutal Completion Date
7. Distribution & Recognition |  |  |  | (Who will receive a copy of the completed form?) (Team and individuals should be formally recognized for the success of the corrective action.)
Distribution List : | [6 empty] | Recognition of Team and Individual Efforts :

## 2. RCCA Worksheet Instructions
|  |  | Root Cause/Corrective Action (RCCA) Worksheet | [9 empty] | Date Issued
1. Build the Team |  |  |  |  | 2. Define the Problem |  |  | (Describe the problem in a concise statement that provides a clear definition of the issue/concern)
Lead
Team Members
3. Containment Action |  | (What immediate action(s) need to be taken to isolate, contain, screen, and provide interim resolution to the problem? Insert additional rows as needed)
Action Items | [6 empty] | Target Completion Date |  |  |  | Responsible Person(s) |  |  | Actual Completion Date
4. Identify Root Cause |  |  |  |  | 4a. Fishbone Diagram |  |  |  | 1) Define and list all contributing factors 2) Highlight in yellow the contributing factors that seem to have the biggest effect 3) Highlight in green the human factors that were considered in the analysis.
| Method |  |  | People |  |  | Environment
Problem / Defect
| Material |  |  | Machine |  |  | Measurement
Fishbone Cause |  |  |  |  | 4b. 3 x 5 Why |  |  |  |  | For each highlighted cause above, perform a 3x5 why analysis
If more than one cause is highlighted, duplicate sections 4b and 4c for each
Direct Cause (What immediate cause led to the nonconformance?)
Detection Cause (Why was the nonconformance not caught by inspection, test, or other process controls?)
Systemic Cause (What core processes, systems, procedures, etc. allowed the nonconformance to occur?)
4c. Identified Root Causes
|  | Direct Root Cause |  |  |  | Detection Root Cause | [5 empty] | Systemic Root Cause
5. Identify and Define Corrective Actions |  |  |  | (Generate permanent corrective action(s) for the identified root causes. Insert additional rows as needed)
Action Items | [6 empty] | Target Completion Date |  |  |  | Responsible Person(s) |  |  | Actual Completion Date
6. Corrective Action Verification Plan |  |  |  | (What actions will be completed to ensure that the corrective action(s) are effective? Insert additional rows as needed)
Corrective Action |  |  |  | How will it be verified? |  |  | Target Completion Date |  |  |  | Responsible Person(s) |  |  | Acutal Completion Date
7. Distribution & Recognition |  |  |  | (Who will receive a copy of the completed form?) (Team and individuals should be formally recognized for the success of the corrective action.)
Distribution List : | [6 empty] | Recognition of Team and Individual Efforts :
Thoroughly define the problem by stating when it was observed, what was observed, where, how much of an impact it has, the expectation not being met, and the desired state.
Assemble a cross functional team that will be working on the project.
Define interim or short term corrective actions to prevent further escapes of defects until permanent corrective actions can be put into place.
"Responsible Person(s)" are the people that will be responsible for task and its completion.
Input the problem / defect that was observed.
Input environmental factors that could have contributed to the problem/defect.
Input human/personnel factors that could have contributed to the problem/defect.
Input process/procedural factors that could have contributed to the problem/defect.
Input material factors that could have contributed to the problem/defect.
Input machine/equipment factors that could have contributed to the problem/defect.
Input measurement/gauge factors that could have contributed to the problem/defect.
When all factors have been listed in the respective fields, highlight the factors that appear to contribute the most to the problem/defect occurring.
Input the date that the corrective action was initiated
The principle behind the 5 Why is to ask "Why" until one cannot ask "why" anymore. The 3 legged 5 Why uses the 5 Why to find three root causes: Direct, Detection, and Systemic.
When "why" cannot be asked further for Direct, Detection, and Systemic causes, input the final answer in the respective root cause boxes.
"Responsible Person(s)" are the people that will be responsible for task and its completion.
"Responsible Person(s)" are the people that will be responsible for task and its completion.
For root causes that were found from Sections 3 and 4, identify and define long term/permanent corrective actions such that the problem/defect will not occur again.
"Actual Completion Date" does not need to be filled out for each corrective action prior to submitting the form for review, if the correcive action will take longer to complete. It is recommended to follow up with Quality once the corrective action has been completed.
Copy corrective actions from Section 5.
Input method for verifying that each corrective action effectively addresses the respective root causes.
"Actual Completion Date" does not need to be filled out for each corrective action prior to submitting the form for review, if the correcive action will take longer to complete. It is recommended to follow up with Quality once the corrective action has been completed.
List out who, internal and external, will receive a copy of the completed form.
Recognizing the team and individuals for the success of the corrective action will help motivate others to participate in other corrective actions.
This section is used to help verify that the corrective actions are effective.
Input the highlighted fishbone cause from 4a that is being analyzed in the 3 x 5 Why. If there are multiple highlighted causes in 4a, duplicate sections 4b and 4c, filling out the fishbone cause for each.
Highlight the human factors that were considered in the analysis. Utilize the Dirty Dozen listed in the procedure.

## 3. RCCA Example
[6 empty] | Root Cause/Corrective Action (RCCA) Worksheet | [11 empty] | Date Issued | 2017-11-07
1. Build the Team | [7 empty] | 2. Define the Problem |  |  |  | (Describe the problem in a concise statement that provides a clear definition of the issue/concern)
Lead |  | Carl Hudson | [5 empty] | Various ACME cases without assignment or status, product not identified for status/function, tubs of parts not identified for status, and boxes of parts not identified for status. In addition, a review of the COLTs print-out of material that is assigned there includes shelf life items that have been expired since 3/3/2013 qty1, 3/5/2013 qty 1, 7/12/2015 qty 3, 7/12/2015 qty 3 (different PN), and 8/31/2012 qty 1. The goal is to resolve the item identification and shelf life item issues within 2 months.
Team Members
James May, Cameron Nolan
3. Containment Action |  |  |  |  | (What immediate action(s) need to be taken to isolate, contain, screen, and provide interim resolution to the problem? Insert additional rows as needed)
Action Items | [10 empty] | Target Completion Date |  |  |  |  | Responsible Person(s) |  |  | Actual Completion Date
Correct COLTS shelf life information for the immediate calibrated equipement out of date. | [10 empty] | 2017-11-22 |  |  |  |  | James May |  |  | 2017-11-22
Label material on the racks outside of the lab. | [10 empty] | 2017-11-22 |  |  |  |  | Carl Hudson |  |  | 2017-11-21
Sort equipment and disposition old engineering equipment. | [10 empty] | 2017-11-22 |  |  |  |  | Carl Hudson |  |  | 2017-11-21
4. Identify Root Cause | [7 empty] | 4a. Fishbone Diagram | [5 empty] | 1) Define and list all contributing factors 2) Highlight the contributing factors that seem to have the biggest effect 3) Highlight in green the human factors that were considered in the analysis.
| Method | [5 empty] | People |  |  |  | Environment
| Multiple Shelf Life Tracking Processes | [5 empty] | Personnel unaware of COLTS shelf life tracking |  |  |  | Storage outside of lab uncontrolled
| Calibration tracked as shelf life | [5 empty] | People do not let go of material at project end |  |  |  | Insufficient storage space in lab
| Shelf Life process EXP567 | [5 empty] | Loss of EMCA Lab Admin |  |  |  | Additional shelf requests denied
[7 empty] | Loss of EMCA Lab Admin backup |  |  |  | Material stored outside of lab | [6 empty] | Problem / Defect
Uncontrolled Engineering material stored outside EMCA Lab Expired shelf life material in COLTS
| Material | [5 empty] | Machine |  |  |  | Measurement
| Equipment from old projects | [5 empty] | COLTS |  |  |  | Shelf Life Report
| Material owned by company | [5 empty] | Storage Racks |  |  |  | Calibration Lab Recall Report
Not all material is tracked in system
Fishbone Cause |  |  | Personnel unaware of COLTS shelf life tracking |  |  |  |  | 4b. 3 x 5 Why | [6 empty] | For each highlighted cause above, perform a 3x5 why analysis
If more than one cause is highlighted, duplicate sections 4b and 4c for each
Direct Cause (What immediate cause led to the nonconformance?)
COLTS showed exipred shelf life material. |  |  |  | EMCA Lab personnel were unaware of shelf life tracking in COLTS. |  |  |  |  | EMCA Lab shelf life material is tracked through in-house procedure PRDB0021 and Calibration Lab recall. |  |  |  | EXP567 and Calibration Lab recall are more comprehensive. |  |  |  |  | Several redundant processes exist for tracking shelf life and calibration information.
Detection Cause (Why was the nonconformance not caught by inspection, test, or other process controls?)
Lab personnel were not aware of notifications of expired material from COLTS. |  |  |  | Notifications were sent to EMCA Lab administrator and were not forwarded to lab personnel. |  |  |  |  | EMCA Lab administrator had left the company and no replacement or back-up was assigned.
Systemic Cause (What core processes, systems, procedures, etc. allowed the nonconformace to occur?)
There are multiple processes / databases for tracking shelf life and calibration information. |  |  |  | The different EMCA sites use different processes for shelf life and calibration. |  |  |  |  | EMCA Lab uses the Sunset Valley process for calibration and a unique database for shelf life instead of COLTS.
4c. Identified Root Causes
[5 empty] | Direct Root Cause |  |  |  |  | Detection Root Cause | [6 empty] | Systemic Root Cause
[5 empty] | Several redundant processes / databases exist for tracking shelf life and calibration. |  |  |  |  | EMCA Lab administrator had left the company and no replacement or back-up was assigned. | [6 empty] | EMCA Lab uses the Sunset Valley process for calibration and a unique database for shelf life instead of COLTS.
Fishbone Cause |  |  | Material stored outside of lab |  |  |  |  | 4b. 3 x 5 Why | [6 empty] | For each highlighted cause above, perform a 3x5 why analysis
If more than one cause is highlighted, duplicate sections 4b and 4c for each
Direct Cause (What immediate cause led to the nonconformance?)
Uncontrolled Engineering material is stored outside the EMCA Lab. |  |  |  | The lab does not have sufficient internal space store everything. |  |  |  |  | Too much old equipment is being stored from older projects. |  |  |  | Material is not dispositioned when a project ends. |  |  |  |  | People want to hold on to the material for future projects.
Detection Cause (Why was the nonconformance not caught by inspection, test, or other process controls?)
Material outside the lab is not controlled. |  |  |  | Majority of the material is found in COLTS. |  |  |  |  | Material is not labled. |  |  |  | Majority of the material is from IRAD projects. |  |  |  |  | IRAD materials are typically not labeled and controlled like demo or production material.
Systemic Cause (What core processes, systems, procedures, etc. allowed the nonconformance to occur?)
The lab does not have sufficient internal space to store all EMCA Lab materials. |  |  |  | There is not enough space on the shelves to store everything inside the lab. |  |  |  |  | The lab has not expanded to support expanded scope of work. |  |  |  | Requests for additional shelves / space have been denied.
4c. Identified Root Causes
[5 empty] | Direct Root Cause |  |  |  |  | Detection Root Cause | [6 empty] | Systemic Root Cause
[5 empty] | People want to hold on to the material for future projects. |  |  |  |  | IRAD materials are typically not labeled and controlled like demo or production material. | [6 empty] | Requests for additional shelves / space have been denied.
5. Identify and Define Corrective Actions | [6 empty] | (Generate permanent corrective action(s) for the identified root causes. Insert additional rows as needed)
Action Items | [10 empty] | Target Completion Date |  |  |  |  | Responsible Person(s) |  |  | Actual Completion Date
Hire new administrator for SUAS Lab | [10 empty] | 2017-11-27 |  |  |  |  | James May |  |  | 2018-01-08
Include COLTS in monthly audit of shelf life material already being completed in accordance with EXP567. | [10 empty] | 2018-01-02 |  |  |  |  | James May |  |  | 2018-01-05
Disposition or reassign equipment at end of project. Limit storage of old equipment to 1 year. | [10 empty] | 2018-02-23 |  |  |  |  | Carl Hudson |  |  | 2018-01-05
Move all storage inside lab, relocate fence. | [10 empty] | 2018-03-02 |  |  |  |  | James May |  |  | 2018-02-16
6. Corrective Action Verification Plan | [6 empty] | .
Corrective Action | [6 empty] | How will it be verified? |  |  |  | Target Completion Date |  |  |  |  | Responsible Person(s) |  |  | Acutal Completion Date
New Admin. | [6 empty] | Follow up with new admin about roles and responsibilities |  |  |  | 2018-03-02 |  |  |  |  | James May |  |  | 2018-02-28
COLTS in Monthly Audit | [6 empty] | Quality to follow-up with lab personnel to go through Monthly Audit process |  |  |  | 2018-03-02 |  |  |  |  | Cameron Nolan |  |  | 2018-03-05
Disposition of equipment | [6 empty] | Review of the quantity of material being stored in the lab |  |  |  | 2018-03-30 |  |  |  |  | Carl Hudson |  |  | 2018-03-29
Move all storage inside lab, relocate fence | [6 empty] | Review of the lab area and verify that no SUAS material is being stored outside of the lab |  |  |  | 2018-04-16 |  |  |  |  | Cameron Nolan |  |  | 2018-04-19
7. Distribution & Recognition | [6 empty] | (Who will receive a copy of the completed form?) (Team and individuals should be formally recognized for the success of the corrective action.)
Distribution List : | [10 empty] | Recognition of Team and Individual Efforts :
Carl Hudson, Cameron Nolan, James May, Kylie Springer, Luke Bower, Max Parr, Hannah Cornish, Kevin Pullman, Fiona Glover | [10 empty] | The team did an outstanding job resolving the audit findings from the third party AS9100/ISO-9001 audit. All team members will be individually recognized through the Sunset Salutes employee recognition program for their hard work and effort working on the project.

## 4. RCCA Flow Chart
Define
Measure
Analyze
Improve
Control
Start
Build the Team (Section 1)
Define the Problem (Section 2)
Define/Implement Containment Action(s) (Section 3)
Is the problem contained?
Gather Data
Is Data Relevant to Problem?
Verify Data
Analyze Data
Is Data Sufficient?
Fill Out Fishbone Diagram (Section 4a)
Determine Root Causes Through 3X5 Why (Section 4b)
Define Corrective Actions For Each Root Cause Found (Section 5)
Do Corrective Actions Dissolve Root Causes?
Define Corrective Action Follow-up Plan (Section 6)
Has the Defined Problem Been Dissolved?
Distribute Finished RCCA Response
Recognize Team and Individual Efforts
End
NO
NO
NO
NO
NO
YES
YES
YES
YES
YES